# Project Planning Phase

Sprint Delivery Plan

| Date | 12 July 2026 |
| --- | --- |
| Team ID | SWTID-2026-4644 |
| Project Name | Smart Lender |
| Phase | 4. Project Planning Phase |

## Sprint Overview

Delivery was organized into 4 sprints of 6 working days each, totalling 59 story points across 8 epics. Team member assignments use role labels rather than named individuals, since no team roster was found in the uploaded project files.

| Sprint | Epic | User Story | Story Points | Priority | Owner |
| --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data Collection & Understanding | Load and profile loan_prediction.csv (nulls, distributions, class balance) | 3 | High | Data/ML Lead |
| Sprint-1 | Data Preprocessing | Handle missing values; encode categorical fields | 6 | High | Data/ML Lead |
| Sprint-1 | Data Preprocessing | Split train/test, scale features, apply SMOTE | 5 | High | Data/ML Lead |
| Sprint-2 | Model Building | Train Decision Tree, Random Forest, KNN, Gradient Boosting | 9 | High | Data/ML Lead |
| Sprint-2 | Model Evaluation | Cross-validate and compare all four models | 3 | High | Data/ML Lead |
| Sprint-2 | Model Selection | Select and persist the best model + scaler | 2 | High | Data/ML Lead |
| Sprint-3 | Application Development | Scaffold Flask app with home/predict/submit routes | 2 | High | Backend Dev |
| Sprint-3 | Application Development | Build application form + server-side encoding | 6 | High | Backend Dev |
| Sprint-3 | Application Development | Wire prediction service into /submit; build result page | 5 | High | Backend Dev |
| Sprint-3 | Frontend Development | Style home, form, and result pages (CSS/JS) | 2 | Low | Backend Dev |
| Sprint-4 | Integration & Testing | End-to-end functional, performance, and UAT testing | 9 | High | Full Team |
| Sprint-4 | Documentation | Finalize requirements.txt and project documentation | 2 | Medium | Full Team |
| Sprint-4 | Deployment Prep | [Proposed] Cloud deployment configuration | 5 | Low | Full Team |

## Definition of Done

- Code is committed and runs without error in a clean environment (pip install -r requirements.txt; python app.py).

- For ML sprints: the notebook runs end-to-end and produces the expected artifact file(s).

- For application sprints: the relevant route/page is reachable and manually verified in a browser.

- For the testing sprint: each story has at least one corresponding test case with a recorded Pass/Fail result.