# Project Planning Phase

Timeline

| Date | 12 July 2026 |
| --- | --- |
| Team ID | SWTID-2026-4644 |
| Project Name | Smart Lender |
| Phase | 4. Project Planning Phase |

## Project Timeline (Gantt Chart)

The Gantt chart below lays out all four sprints against calendar dates, along with two key milestones (MVP feature-complete and testing sign-off), consistent with Project_Milestones.docx and Sprint_Delivery_Plan.docx.

Figure 1: Smart Lender Project Timeline — 4 sprints across 24 working days (01 Jun – 27 Jun 2026).

## Timeline Summary

| Period | Focus | Key Output |
| --- | --- | --- |
| 01–06 Jun 2026 | Data Collection & Preprocessing | Cleaned, encoded, SMOTE-balanced dataset |
| 08–13 Jun 2026 | Model Building & Evaluation | Selected and persisted Random Forest model |
| 15–20 Jun 2026 | Application Development | Working Flask app (MVP feature-complete milestone) |
| 22–27 Jun 2026 | Integration, Testing & Documentation | Verified test results (testing sign-off milestone) |

## Critical Path

Model Building (Sprint 2) is on the critical path: Application Development (Sprint 3) cannot wire in a real prediction until the model and scaler artifacts exist, and Testing (Sprint 4) cannot validate real predictions until the application is feature-complete. Any delay in Sprint 2 would cascade through Sprints 3 and 4 under this plan.

## Buffer & Contingency

No explicit buffer days were built into this 24-day plan; each sprint's 6 days map directly to its story-point load. For a real-world rerun of this schedule, a 1–2 day buffer between Sprint 2 and Sprint 3 would reduce the critical-path risk identified above, since model comparison notebooks can take longer than expected if cross-validation reveals the need for additional hyperparameter tuning.

## Comparison to Actual Delivery

Because this documentation was produced by reviewing a complete, working codebase rather than observing a project in progress, the 'actual' dates in this timeline are a reconstructed, plausible schedule consistent with the final deliverable — not a captured historical record. This limitation is also flagged in the Phase Completion Report for the Project Planning Phase.

## Relationship to Other Planning Documents

- Project_Milestones.docx defines the checkpoints this timeline schedules.

- Sprint_Delivery_Plan.docx defines the story-level work packed into each of the four sprint bars shown above.

- Project_Progress_Tracking.docx reports the same four sprints' story-point completion and velocity.